## excel
/Non Project/PSP Fundamentals & Advanced/Program 5
PSP2.1 Project Plan Summary
Project Settings
Project Owner | Juan Pablo Ospino Solano
Start Date | abr 02, 2017 05:25:55 PM
Completion Date | abr 03, 2017 09:00:10 PM |  |  |  | Completed: *
Keywords | Tarea 5 finalizada
Language | Java
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 27.1 | 20.9 | 28.1
Planned Time | 0.13264 |  | 1899-12-31 02:00
Actual Tiempo |  | 0.25903 | 1899-12-31 09:07
CPI (Cost-Performance Index) |  |  | 0.79
% Reuse | 0% | 0% | 1.68%
% New Reusable | 0% | 0% | 6.24%
Test Defects/KLOC or equivalent | 1.25 | 0 | 1.08
Total Defects/KLOC or equivalent | 15 | 46.2 | 19.4
Yield % | 83.3% | 83.3% | 83.3%
Code Review Rate | 1989 | 260 | 1072
% Appraisal COQ | 2.17% | 13.4% | 4.28%
% Failure COQ | 4.65% | 4.56% | 4.63%
COQ A/F Ratio | 0.47 | 2.94 | 0.92
PQI | 0 | 0.11 | 0
Program Size
| Plan | Actual | A la Fecha
Base (B) | 0 | 0 | 0
Deleted (D) | 0 | 0 | 0
Modified (M) | 0 | 0 | 0
Added (A) | 86.2 | 130 | 929
Reused (R) | 0 | 0 | 11
Added and Modified (A+M) | 86.2 | 130 | 929
Total Size (T) | 86.2 | 130 | 656
Total New Reusable | 0 | 0 | 58
Estimated Proxy Size (E) | 80.9 | 130 | 543
Upper Prediction Interval (70%) | N/A
Lower Prediction Interval (70%) | N/A
Time In Phase
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.018056 | 0.061806 | 0.21528 | 15.6%
DiseÃ±o | 0.0048611 | 0.034722 | 0.072917 | 5.28%
RevisiÃ³n de DiseÃ±o | 0.0013889 | 0.013889 | 0.022917 | 1.66%
CodificaciÃ³n | 0.089583 | 0.10417 | 0.86319 | 62.6%
RevisiÃ³n de CodificaciÃ³n | 0.0020833 | 0.020833 | 0.036111 | 2.62%
CompilaciÃ³n | 0.0027778 | 0.00069444 | 0.021528 | 1.56%
Pruebas | 0.0034722 | 0.011111 | 0.042361 | 3.07%
Postmortem | 0.011111 | 0.011806 | 0.10556 | 7.65%
Total | 0.13264 | 0.25903 | 1899-12-31 09:07
Total Time UPI (70%) | 0.24722
Total Time LPI (70%) | 0.018056
Defects Injected
| Plan | Actual | A la Fecha | % A la Fecha
Antes de Desarrollo | 0 | 0 | 0 | 0%
PlaneaciÃ³n | 0 | 0 | 0 | 0%
DiseÃ±o | 0.43 | 2 | 6 | 33.3%
RevisiÃ³n de DiseÃ±o | 0 | 0 | 0 | 0%
CodificaciÃ³n | 0.86 | 4 | 12 | 66.7%
RevisiÃ³n de CodificaciÃ³n | 0 | 0 | 0 | 0%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0 | 0 | 0 | 0%
Total | 1.3 | 6 | 18
Defects Removed
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0 | 0 | 0 | 0%
DiseÃ±o | 0 | 0 | 0 | 0%
RevisiÃ³n de DiseÃ±o | 0.11 | 0 | 1 | 5.56%
CodificaciÃ³n | 0.76 | 2 | 9 | 50%
RevisiÃ³n de CodificaciÃ³n | 0.22 | 3 | 5 | 27.8%
CompilaciÃ³n | 0.11 | 1 | 2 | 11.1%
Pruebas | 0.11 | 0 | 1 | 5.56%
Total | 1.3 | 6 | 18
After Development | 0 | 0 | 6
Defect Removal Efficiency
| Plan | Actual | A la Fecha
Defects/Hour - Design Review | 4.21 | 0 | 1.82
Defects/Hour - Code Review | 4.98 | 6 | 5.77
Defects/Hour - Compile | 1.83 | 60 | 3.87
Defects/Hour - Test | 1.22 | 0 | 0.98
DRL (DLDR/UT) | 3.46 | 0 | 1.85
DRL (Code Review/UT) | 4.09 | 6.1 | 5.87
DRL (Compile/UT) | 1.5 | 61 | 3.94
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 09:29 PM el 3/04/2017